## Web July 08
Labor Estimate-to-Actual Comparison
Enter data into white cells only. Shaded cells contain formulas.
MILLER JOB | Estimate |  |  | Cost |  |  | Difference
Labor only: | Hrs | Rate | Total Est $ | Hrs | Rate | Total Est $ | Hrs | Rate | Total Est $
Supervision | 20 | 40 | 800 | 24 | 36 | 864 | 4 | -4 | 64
Demolition | 6 | 40 | 240 | 8 | 22 | 176 | 2 | -18 | -64
Finish carpentry | 8 | 40 | 320 | 12 | 32 | 384 | 4 | -8 | 64
Clean up | 6 | 40 | 240 | 9 | 20 | 180 | 3 | -20 | -60
Total | 40 |  | 1600 | 53 |  | 1604 | 13 | 30.2642 | 4
The spreadsheet above compares labor costs for a single project.
You can combine results from several projects into a single table.
You can also add orremove tasks from the list in Col. A
Estimate
Users enter estimated man-hours into Col. B and rate of pay in Col. C.
Total estimated man-hours and total estimated cost for the work is
automatically calculated in Row 9.
Cost
Users enter actual man-hours into Col. E and actual rate of pay in Col. F.
Total actual man-hours and total actual cost for the work is
automatically calculated in Row 9.
Difference
Formulas calculate the difference between estimated man-hours and
estimated costs in Row 9.
Blue Cells
Variations in man-hours and costs should both be checked. In this example,
the project actually took about 33% more time to complete. But because the
$40 estimated labor rate is inflated, the loss on the project was contained.
In fact, however, the project was badly mis-estimated; in effect, a one week
job took 7 days to complete. Had it been a four week job, it would have run
a week over schedule.
By comparing historical labor data, both man-hours and dollar cost,
you can improve the accuracy of your estiamtes and gain a better
understanding of actual productivity rates.